## REQUIREMENT MATRIX
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: | Nathan Rameses Balois |  |  | PROJECT ID: |  | AX-EMEA-000302
PROJECT SPONSOR: | Bernadettte Sison |  |  | PROJECT TITLE: |  | SA Hub
REQUIREMENT INFORMATION | [5 empty] | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | SOURCE | TRACEABILITY ID | BUSINESS OBJECTIVE | DELIVERABLE(S) | VERFICATION | VALIDATION | TEST CASE ID
REQ-001 | Should Have | Ability for SAs to easily receive tasks based on their course program. | Medium | Student Assistant | 1 | Gain program related experiences from task assigned | Tasks assigned based on SA's program, task details | Tasks are assigned based on program | Receive tasks on task page based on his/her course program. | TC-001 - Program-based task assignment
REQ-002 | Should Have | Ability for SAs to render during vacant time based on academic schedule. | Medium | Student Assistant | 2 | Better time management for SA | Tasks assigned based on SA's vacant time, task details | Tasks are assigned based on academic schedule | Test task assignment with vacant time | TC-002 - Schedule-based task assignment
REQ-003 | Could Have | Ability for SAs to volunteer for advanced rendering task. | Low | Student Assistant | 3 | SA can finish required hours and gain more experience | Voluntary task assignment system | Voluntary tasks are assigned | Test voluntary task assignments | TC-003 - Voluntary task assignment
REQ-004 | Must Have | Ability for SAs to automatically record all the task including task details and total hours. | High | Student Assistant | 4 | SA avoids having to write tasks manually on a log sheet | System for automatically recording tasks and hours | System logs all task history | Test task logging system | TC-004 - Task logging system
REQ-005 | Must Have | Ability for SAs to view their scholarship status | High | Student Assistant | 5 | SA knows if they can still receive SA duties | System showing SA's scholarship status | Scholarship status is visible and up to date | Test scholarship status update and display | TC-005 - Status update and display
REQ-006 | Must Have | Ability for SA Manager to see reports about SAs and offices | High | SA Manager | 6 | SA Manager can monitor SA and office tasks better | Reports for monitoring SAs and offices | Comments are added to scholarship records | Test report generation for SAs and offices | TC-006 - SAs and office reports
REQ-007 | Must Have | Ability for SA Manager to see the status of the task | High | SA Manager | 7 | SA Manager can monitor and track task progress and completion | Task progress tracking system | Task status is updated and viewable in real-time | Test task status updates | TC-007 - Task status update
REQ-008 | Must Have | Ability for Manager to see office feedback on SAs assigned | High | SA Manager | 8 | SA Manager can monitor feedback and assign SAs more effectively | Office feedback system and assignment tool | Feedback and task reassignments are processed | Test feedback entry and reassignment | TC-008 - Feedback and reassignment
REQ-009 | Could Have | Ability for SA Manager to checked hours rendered by SAs | Low | SA Manager | 9 | SA Manager ensures the hours rendered match the time in and out | SA hours management system | SA hours are correctly calculated | Test SA hours calculation system | TC-009 - Calculation hours of the SAs
REQ-010 | Must Have | Ability for Requesting Office to request SAs to help with tasks | High | Requesting Office | 10 | Requesting office can finish tasks faster | Task assignment system for offices | Tasks are assigned to the correct SA | Test task assignment functionality | TC-010 - Assignment functionality
REQ-011 | Must Have | Ability for Requesting Office to request SAs with specific course programs | High | Requesting Office | 11 | Offices can assign SAs with relevant knowledge | Task assignment based on course programs | SA assignments are made based on course program | Test course program match during SA assignment | TC-011 - Match of course program
REQ-012 | Could Have | Ability for Requesting Office to send feedback on assigned SAs | Low | Requesting Office | 12 | Offices can rate the work of assigned SAs | Feedback form for SA performance | Feedback is submitted for each assigned SA | Test feedback submission process | TC-012 - Feedback process
REQ-013 | Could Have | Ability for Guidance Counselor to view scholarship status of all SAs via dashboard | High | Guidance Counselor | 13 | Guidance Counselor can monitor SA compliance and eligibility | Scholarship status dashboard | Dashboard displays scholarship status | Test scholarship status display on dashboard | TC-013 - Status display on dashboard
REQ-014 | Must Have | Ability for Guidance Counselor to manage SAs scholarship status after consultation | High | Guidance Counselor | 14 | Guidance Counselor can confirm or cancel SA's scholarship status | Scholarship management system | Scholarship status is confirmed or canceled | Test scholarship confirmation and cancellation | TC-014 - Confirmation and cancellation of scholarship
REQ-015 | Could Have | Ability for Guidance Counselor to add comments or reasons for revoking scholarship | Low | Guidance Counselor | 15 | Guidance Counselor can provide reasons for revoking scholarships | Comment system for scholarship records | Comments are added to scholarship records | Test comment addition and visibility on scholarship records | TC-015 - Scholarship records
REQ-016 | Must Have | Ability for Office to receive nofications for assigned SA scholarship revocation | High | Requesting Office | 16 | Requesting Office can receive notifications when SA assigned to their task got their scholarship revoked | Display notification and scholarship status | Receive notification after assigned SA scholarship revocation | Test display of notifications after | TC-016 - Notify SA Revocation

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
REQUIREMENT ID
Give each requirement a unique identifier or reference so that it can be easily traced throughout the project life-cycle.
CATEGORY
Provide a category for the requirement typical categories are: functional, non-functional, usability, security, performance, maintainability etc.
REQUIREMENT
Describe the requirement that needs to be met by the project. The requirement might be a product, some product functionality, a service, or a result.
PRIORITY
Provide a priority for the requirement. For example, mandatory, should have, nice to have or high, medium, low.
SOURCE
Enter the name of the stakeholder that identified the requirement.
BUSINESS OBJECTIVE
Document the business objective that this requirement will meet or help to meet. The business objective will come from the project charter or the Project business Case.
DELIVERABLE(S)
List the deliverable or deliverables that will make up this requirement.
TRACEBILITY ID
The identifier that relates the validation and verification to the requirements.
VERIFICATION
Explain how you will test that the requirement is completed satisfactorily. For example 99.9% uptime for user acceptance of software.
VALIDATION
Explain how the requirement will be validated or tested. This will often be via user acceptance testing, but it might also be by the achievement of a milestone or perhaps by the completion of a key performance indicator.
TEST CASE ID
A Test Case identifier is referenced by the test design specification and the test procedure specifications. which identify a test case uniquely.

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Supplier - On projects with multiple suppliers you may want to add a field to note the supplier responsible.
WBS ID - Add WBS ID so that the requirement can be linked to the Work Breakdown Structure and project schedule.
Test case ID - Later in the project you may want to link the requirement to the test cases that will be used to
check that the requirement meets the business objective.